|  |  |
| --- | --- |
| Project Update Meeting | |
| Location: | University of the Witwatersrand, Chamber of Mines |
| Date: | 09 August 2019 |
| Time: | 10:00 |
| Facilitator: | Prof. F Takawira |

# Agenda Items & Discussion Points

1. Update Prof. since the last meeting.
2. Confirm how to set up channel and channel coding.
3. Covered the entire block diagram and implementation in discussion.
4. Discussed the holes creation and filling methodology again.

|  |  |  |  |
| --- | --- | --- | --- |
| Action Items | Owner(s) | Deadline | Status |
| Tweak DCT implementation | Kishan Narotam & Nitesh Nana | 26 July 2019 | Completed |
| Create Implementation for holes only | Kishan Narotam & Nitesh Nana | 26 July 2019 | Completed |
| Start encoding using run-length encoding | Kishan Narotam & Nitesh Nana | 02 August 2019 | In Progress |
| Research and find a reason for Chebyshev distance | Kishan Narotam & Nitesh Nana | 26 July 2019 | Completed |
| Pull equation used to  fill holes | Kishan Narotam & Nitesh Nana | 09 August 2019 | In Progress |
| Create a simple channel | Kishan Narotam & Nitesh Nana | 09 August 2019 | Needs to be started |
| Introduce errors | Kishan Narotam & Nitesh Nana | 09 August 2019 | Needs to be started |